## Sheet1
|  | TASK | TASK | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 (MID TERM SUBMISSION) |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18 |  |  |  |  | WEEK 19 |  |  |  |  | WEEK 20 |  |  |  |  | WEEK 21 |  |  |  |  | WEEK 22 (FINALS SUBMISSION)
LEGEND |  | ID | TITLE | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | R | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
| % Completion | TASK ID: 1; TASK TITLE: Bubble Chart Extension; WEEK 10 M: X; WEEK 10 T: X; WEEK 10 W: X; WEEK 10 T: X; WEEK 10 F: X; WEEK 11 M: X; WEEK 11 T: X; WEEK 11 W: X; WEEK 11 T: X; WEEK 11 F: X
| Hours Spent | TASK ID: 1.1; TASK TITLE: Data; WEEK 10 M: Completion:; WEEK 10 T: 100%; WEEK 12 (MID TERM SUBMISSION) M: Date - Line; WEEK 22 (FINALS SUBMISSION) M: Date - Line
| Submission | TASK ID: 1.1.1; TASK TITLE: Find Suitable Data and Clean; WEEK 10 M: 3hr
| Hours Planned | TASK ID: 1.1.2; TASK TITLE: Code Planning/ Find Suitable Visualisation for Data; WEEK 10 T: 2hr
| Unable to Implement | TASK ID: 1.2; TASK TITLE: Development; WEEK 10 W: Completion:; WEEK 10 F: 100%
|  | 1.2.1 | Research coding techniques |  | 2hr
|  | 1.2.2 | Coding |  | 7hr | 1hr
|  | 1.2.2.1 | - Axis, labels and selectors |  |  | 1hr
|  | 1.2.2.2 | - Bubble object |  |  |  | 1hr
|  | 1.2.2.3 | - Infographics |  |  |  | 6hr
|  | 1.2.3 | Debugging and refractoring |  |  |  | 2hr | 4hr
|  | 1.3 | Finalisation (Mid Term) | [7 empty] | Completion: |  | 100%
|  | 1.3.1 | Documentation and logging of work done | [5 empty] | 5hr | 2hr
|  | 1.3.2 | Evaluation and reflection | [6 empty] | 5hr | 3hr
|  | 1.3.3 | Head room for unforseen problems | [7 empty] | 3hr | 3hr | 5hr
|  | 1.4 | Code Correction | [19 empty] | Completion: 100%
|  | 1.4.1 | Refractor Codes | [11 empty] | 2hr | 2hr | 2hr | 2hr | 1hr
|  | 1.4.2 | Code Optimisation | [16 empty] | 2hr | 3hr | 2hr | 2hr | Buffer
|  | 1.5 | Functional Improvement | [47 empty] | Completion: 100%
|  | 1.5.1 | Research on Additional Improvements (UI & Ease of use) | [21 empty] | 2hr | 3hr
|  | 1.5.2 | Planning Additional Functions | [23 empty] | 3hr | 3hr
|  | 1.5.3 | Implemntation of codes | [25 empty] | 2hr | 2hr | 2hr | 2hr
|  | 1.5.3.1 | - Inforgraphic Bar | [29 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 1.5.3.2 | - Fix Filtering for drop down | [32 empty] | 1hr | 1hr | 1hr
|  | 1.5.3.3 | - Timeline Slider | [35 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 1.5.4 | - Miscellaneous Addition 1) Add Axis Labels 2) Add Grid Lines | [54 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 1.5.5 | Error Handling and Validation | [38 empty] | 1hr | 1hr | 1hr
|  | 1.5.6 | Debugging | [41 empty] | 2hr | 2hr
|  | 1.5.7 | Testing (Stability and Reliability) | [43 empty] | .5hr | .5hr
|  | 1.6 | Finalisation (Finals) | [58 empty] | Completion:
|  | 1.6.1 | Documentation and logging of work done | [45 empty] | 1hr | 1hr | 1hr
|  | 1.6.1.1 | Evaluation & Reflection | [48 empty] | 1hr | 1hr | 1hr
|  | 1.6.2 | Code Mordularity and Resuseability | [51 empty] | 3hr | 3hr | 3hr
|  | 1.6.3 | Final Review | [53 empty] | 2hr | 2hr
|  | 1.6.4 | 1 Week Buffertime for unresolved problems | [55 empty] | Buffer | Buffer | Buffer | Buffer | Buffer
|  | 2 | Sortable Bar Chart Extension
|  | 2.1 | Data | 100% | [9 empty] | Date - Line | [49 empty] | Date - Line
|  | 2.1.1 | Find and clean up suitable data set | 3hr
|  | 2.1.2 | Brainstorm UI design and code planning | 2hr
|  | 2.2 | Development |  |  |  |  | 100%
|  | 2.2.1 | Research coding techniques |  | 2hr
|  | 2.2.2 | Coding |  | 6hr | 3hr
|  | 2.2.2.1 | Axis, labels and selectors |  |  | 1hr
|  | 2.2.2.2 | Search and sort algorithm |  |  |  | 1hr
|  | 2.2.2.3 | Bar object |  |  |  | 6hr | 2hr
|  | 2.2.3 | Debugging and refractoring |  |  |  |  | 4hr
|  | 2.3 | Finalisation (Mid Term) | [9 empty] | 100%
|  | 2.3.1 | Documentation and logging of work done | [5 empty] | 5hr | 2hr
|  | 2.3.2 | Evaluation and reflection | [6 empty] | 5hr | 3hr
|  | 2.3.3 | Head room for unforseen problems | [7 empty] | 3hr | 3hr | 5hr
|  | 2.4 | Code Correction | [19 empty] | 100%
|  | 2.4.1 | Refractor Codes | [11 empty] | 2hr | 2hr | 2hr | 2hr | 1hr
|  | 2.4.2 | Code Optimisation | [16 empty] | 2hr | 3hr | 2hr | 2hr | Buffer
|  | 2.5 | Functional Improvement | [48 empty] | 100%
|  | 2.5.1 | Research on Additional Improvements (UI & Ease of use) | [21 empty] | 2hr | 3hr
|  | 2.5.2 | Planning Additional Functions | [23 empty] | 2hr | 2hr
|  | 2.5.3 | Implemntation of codes | [25 empty] | 2hr | 2hr | 2hr | 2hr
|  | 2.5.3.1 | - Mouse Hover Information | [29 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 2.5.3.2 | - More Imformative Bar | [32 empty] | 1hr | 1hr | 1hr
|  | 2.5.3.3 | - Miscellaneous Addition 1) Fix the percentage bar 2) Add in data of "Rest of the world" 3) Fix "Selected year" year as displays the flipped year | [35 empty] | 1.5hr | 1.5hr | 1.5hr | [15 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 2.5.4 | Error Handling and Validation | [38 empty] | 1hr | 1hr | 1hr
|  | 2.5.5 | Debugging | [41 empty] | 2hr | 2hr
|  | 2.5.6 | Testing (Stability and Reliability) | [43 empty] | .5hr | .5hr
|  | 2.6 | Finalisation (Finals) | [58 empty] | Completion:
|  | 2.6.1 | Documentation and logging of work done | [45 empty] | 1hr | 1hr | 1hr
|  | 2.6.1.1 | Evaluation & Reflection | [48 empty] | 1hr | 1hr | 1hr
|  | 2.6.2 | Code Mordularity and Resuseability | [51 empty] | 3hr | 3hr | 3hr
|  | 2.6.3 | Final Review | [53 empty] | 2hr | 2hr
|  | 2.6.4 | 1 Week Buffertime for unresolved problems | [55 empty] | Buffer | Buffer | Buffer | Buffer | Buffer
|  | 3 | Candle Stick Chart Extension
|  | 3.1 | Data | 100% | [9 empty] | Date - Line | [49 empty] | Date - Line
|  | 3.1.1 | Find and clean up suitable data set | 3hr
|  | 3.1.2 | Brainstorm UI design and code planning | 2hr
|  | 3.2 | Development |  |  |  |  | 100%
|  | 3.2.1 | Research coding techniques |  | 2hr
|  | 3.2.2 | Coding |  | 6hr | 3hr
|  | 3.2.2.1 | Data structure |  |  | 1hr
|  | 3.2.2.2 | Mapping data strcuture to circle |  |  |  | 1hr
|  | 3.2.2.3 | Animation |  |  |  | 6hr
|  | 3.2.3 | Debugging and refractoring |  |  |  | 2hr | 4hr
|  | 3.3 | Finalisation (Mid Term) | [9 empty] | 100%
|  | 3.3.1 | Documentation and logging of work done | [5 empty] | 5hr | 2hr
|  | 3.3.2 | Evaluation and reflection | [6 empty] | 5hr | 3hr
|  | 3.3.3 | Head room for unforseen problems | [7 empty] | 3hr | 3hr | 5hr
|  | 3.4 | Code Correction | [19 empty] | 100%
|  | 3.4.1 | Refractor Codes | [11 empty] | 2hr | 2hr | 2hr | 2hr | 1hr
|  | 3.4.2 | Code Optimisation | [16 empty] | 2hr | 3hr | 2hr | 2hr | Buffer
|  | 3.5 | Functional Improvement | [48 empty] | 100%
|  | 3.5.1 | Research on Additional Improvements (UI & Ease of use) | [21 empty] | 2hr | 3hr
|  | 3.5.2 | Planning Additional Functions | [23 empty] | 2hr | 2hr
|  | 3.5.3 | Implemntation of codes | [25 empty] | 2hr | 2hr | 2hr | 2hr
|  | 3.5.3.1 | - Horizontal Movable Slider | [29 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 3.5.3.2 | - Zoom Slider | [32 empty] | 1hr | 1hr | 1hr
|  | 3.5.3.3 | - Miscellaneous Addition 1) Graph Stability 2) Zoom Label | [32 empty] | 1hr | 1hr | 1hr | [17 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 3.5.3.4 | - Fix Informative Date Function | [35 empty] | 1.5hr | 1.5hr | 1.5hr
|  | 3.5.4 | Error Handling and Validation | [38 empty] | 1hr | 1hr | 1hr
|  | 3.5.5 | Debugging | [41 empty] | 2hr | 2hr
|  | 3.5.6 | Testing (Stability and Reliability) | [43 empty] | .5hr | .5hr
|  | 3.6 | Finalisation (Finals) | [58 empty] | Completion:
|  | 3.6.1 | Documentation and logging of work done | [45 empty] | 1hr | 1hr | 1hr
|  | 3.6.1.1 | Evaluation & Reflection | [48 empty] | 1hr | 1hr | 1hr
|  | 3.6.2 | Code Mordularity and Resuseability | [51 empty] | 3hr | 3hr | 3hr
|  | 3.6.3 | Final Review | [53 empty] | 2hr | 2hr
|  | 3.6.4 | 1 Week Buffertime for unresolved problems | [55 empty] | Buffer | Buffer | Buffer | Buffer | Buffer
|  | 4 | Geographic Projection on Map Extension
|  | 4.1 | Data
|  | 4.1.1 | Find and clean up suitable data set
|  | 4.1.2 | Brainstorm UI design and code planning
|  | 4.2 | Development
|  | 4.2.1 | Research D3 library
|  | 4.2.2 | Coding
|  | 4.2.2.1 | KIV
|  | 4.2.2.2 | KIV
|  | 4.2.2.3 | KIV
|  | 4.2.3 | Debugging and refractoring
|  | 4.3 | Finalisation
|  | 4.3.1 | Documentation and logging of work done
|  | 4.3.2 | Evaluation and reflection
|  | 3.4 | Head room for unforseen problems
|  | 5 | User Interface
|  | 5.1 | Research
|  | 5.1.1 | Research common UI design practices
|  | 5.2 | Development
|  | 5.2.1 | Implement and refractor code
|  | 6 | Design Pattern
|  | 6.1 | Research
|  | 6.1.1 | Research JavaScript design patterns
|  | 6.2 | Development
|  | 6.2.2 | Implement and refractor code
2 weeks buffer between completion and submission